## Slide 2: Project title: Analysing shovel-dumper productivity for coal mine

## Slide 3: Objective of study
To estimate normative productivity of shovel-dumper combination with different material characteristic and different equipment combination.
To validate the normative productivity with the actual productivity of similar equipment combination in certain selected coal mine.
To analyse the reasons for variation between normal and actual productivity in different cases.
To give suggestion for improvement in the productivity of shovel dumper system.

## Slide 4: Background of study
The study was conducted for sonepur bazari of ECL considering the actual performance data of 2011-12 for Shovel-Dumper operation.
The project deploys both departmental and hired equipments. The study was only conducted for departmental equipment(Shovel-Dumper).
The productivity of shovel dumper considered in approved project report of sonepur bazari OCP(3.4mt capacity) was compared with the actual shovel-Dumper productivity obtained in the mine.

## Slide 5
Norms and methodology for the calculation of the productivity of Shovels and dumpers

## Slide 6: Catagorisation of material
Compressive strength(KG/Sq. CM) | Category | Blasting required
Up to 55 | I | NIL
>55 & up to 125 | II | NIL
>125 & up to 250 | III | LIGHT
250 & up to 1250 | IV | FULL
>1250 | V | FULL

## Slide 7: Electric rope shovel bucket cycle time
Category of the material to be excavated | Cycle time (Minutes) for 90 degree swing angle | Cycle time(Minutes) for 180 degree swing angle
I | .44 | .55
II | .47 | .58
III | .50 | .61
IV | .53 | .64
V | .56 | .67

## Slide 8: Hydraulic shovel bucket cycle time
Category of the material to be excavated | Cycle time (Minutes) for 90 degree swing angle | Cycle time(Minutes) for 180 degree swing angle
I | .42 | .49
II | .44 | .51
III | .46 | .53
IV | .48 | .55
V | .50 | .57

## Slide 9: Shovel bucket fill factor
Category of the material to be excavated | Fill factor for 3cubic mt. bucket | Fill factor for 13cubic mt. bucket
I | .95 | 1.05
II | .925 | 1.025
III | .90 | 1.00
IV | .875 | .99
V | 85. | .95

## Slide 10: Swell factor of the material to be excavated
Category of material | Swell factor
I | 0.80
II | 0.77
III | 0.735
IV | 0.705
V | 0.67

## Slide 11: Shovel time between Dumper loadings for spotting of dumper
Rear Dumper capacity(Tn) | Minutes
35 | .5
45 | .51
55 | .522
65 | .534
75 | .546
85 | .56
120 | .60

## Slide 12: Average Dumper Speed
Lead(KM) | Average speed for Mechanical wheel drive(KM./HR.) | Average speed for Electrical wheel drive(KM./HR.)
0.5 | 13 | 14
1.0 | 16 | 18
1.5 | 18 | 20
2.0 | 20 | 22
2.5 | 22 | 24
3.0 | 23 | 25
3.5 | 24 | 26

## Slide 13: Standard availability of Dumpers
Dumpers | Shifts | Availability%
Mechanical | 3 | 67
 | 2 | 87
Electro wheel drive | 3 | 72
 | 2 | 89

## Slide 14: Normative case study( for O/B)
Calculation for productivity of shovel and dumper
SL. No. | Particulars | 10 cu.m. Electric rope shove+120 ton. Dumper
1 | Dumper pay load(Tns) | 108.970
2 | Assumed category of rock | 50% of category III+50% of category IV
3 | Swell factor | 0.719
4 | Bucket fill factor | 0.958
5 | Swell cum bucket fill factor(3x4) | 0.689
6 | Bucket capacity(CUM) | 10.000
7 | Solid bucket capacity(5x6 CUM) | 6.898

## Slide 15
SL. No. | Particulars | 10 cu.m. Electric rope shove+120 ton. Dumper
8 | Volume weight(TE/CUM) | 2.4(Assumed)
9 | Solid capacity of Dumper for Full pay load (1/8 CUM) | 45.404
10 | Loose capacity of Dumper for pay-Load(9/3 CUM) | 63.149
11 11A | Struck capacity of Dumper(CUM) Heaped capacity of Dumper(CUM) | 60.000 80.000
12 | Solid capacity of Dumper(cum.) | 41.340
13 | Number of buckets per Dumper(12/7) | 5.99=6
14 | Load per Dumper(13*7 CUM) | 41.34

## Slide 16
SL. No. | Particulars | 10 cu.m. Electric rope shove+120 ton. Dumper
15 | Bucket cycle time (MIN.) | 0.625
16 | Direct Loading time (13x15MIN.) | 3.750
17 | Time for placement of 1 Dumper(MIN.) | 0.600
18 | Total time for loading 1 Dumper (16+17 Min.) | 4.350
19 | Hourly output per Shovel(60x14/18 cum) | 570.207
20 | Factor for travel, position etc. | 0.80
21 | Average standard hourly output(19x20Cum.) | 456.166

## Slide 17
SL. No. | Particulars | 10 cu.m. Electric rope shove+120 ton. Dumper
22 | Spotting, Loading, Waiting time (min.) | 3.4
23 | Annual Shift hours | 7200
24 | Average standard utilisation % | 58
25 | Average standard utilised hours | 4158
26 | Annual output/Shovel(25x21 M.cum.) | 1.897
27 | Annual productivity adopted for project planning/Shovel(M.Cum.) | 1.890

## Slide 18: Calculation for productivity and requirements of Dumpers per shovel
Sl. NO. | Details | Unit | 10. cum. Electric shovel with 120 ton. Dumper.
1 | Lead | KMS | 0.5 1.0 1.5 2.0 2.5 3.0 3.5
2 | Average Dumper speed | KM/HR | 13 16 18 20 22 23 24
3 | Dumper travel time | Minutes | 4.615 7.5 10 12 13.636 15.652 17.5
4 | Dumper spotting, unloading and waiting time | Minutes | 3.4 3.4 3.4 3.4 3.4 3.4 3.4
5 | Dumper loading time | Minutes | 3.75 3.75 3.75 3.75 3.75 3.75 3.75
6 | Total Dumper cycle time | Minutes | 11.765 14.650 17.150 19.150 20.786 22.802 24.65
7 8 | Total Dumper loading time No. of Dumpers to work with 1 shovel(6/7) | MIN. UNITS | 4.35 4.35 4.35 4.35 4.35 4.35 4.35 2.705 3.368 3.943 4.40 4.778 5.24 5.66

## Slide 19: On 3 shifts per day basis
Sl. No. | Details | Units | 10. cum. Electric shovel with 120 ton. Dumper.
9 | Working Dumper avalibality | % | 67 67 67 67 67 67 67
10 | Population of dumpers with 1 working shovel (8/9) | Nos. | 4.037 5.027 5.885 6.570 7.131 7.821 8.448
11 | Annual productivity of dumper | M.CUM. | 0.4682 0.3760 0.3212 0.2877 0.2650 0.2417 0.2237

## Slide 20
 |  | Unit |  |  | 
 |  |  | Total | Out sourced | dept.
Coal |  | Mt | 5.15 | 1.75 | 3.4
OB |  |  |  |  | 
 | S/D | Mcum | 23.1 | 14.6 | 8.5
 | D/L |  | 3.04 |  | 3.04
 |  | TOTAL | 26.14 | 14.6 | 11.54
Sp.Gr | 1.4 | t/cum
Stripping ratio | 5.07 | cum/t
SONEPUR BAZARI Project report data

## Slide 21
 | System factor as in Project Report |  | 
Machine | Work load as in PR | Digging capacity as in PR | System factor
Shovel | 10.9286 | 18.01 | 0.6068

## Slide 22
LEAD | COAL | 3 | KM
 | OB | 2.5 | 
Wt LEAD |  | 2.61111111 | 
Lead from operational plan for 2011-12

## Slide 23: Calculation of Dumper factor
Dumper factor is defined as
DF=
=1.17

## Slide 24: Normative Vs. Actual avail. & Util. Sonepur Bazari
Equipment | CIL Norms |  | Progressive up to March 2011 |  | Progressive up to March 2012 | 
 | Avail | Util. | Avail | Util. | Avail | Util.
SHOVEL | 80 | 58 | 73.11 | 41.46 | 69.97 | 42.46
5cum/4.6B/5A | 80 | 58 | 68.14 | 17.95 | 69.28 | 24.32
10cum/1900AL P&H | 80 | 58 | 72.32 | 49.97 | 71.93 | 51.19
Hydraulic | 80 | 58 | 76.25 | 40.58 | 67.81 | 39.66
DUMPER | 67 | 50 | 60.60 | 43.51 | 59.68 | 40.59
50t(All Dumper) | 67 | 50 | 61.25 | 45.04 | 56.03 | 40.59
BH50M-1 60T | 67 | 50 | - | - | 72.94 | 52.37
BH100 100T | 67 | 50 | - | - | 83.14 | 57.17
120t/445E | 72 | 55 | 60.15 | 42.22 | 54.92 | 34.68

## Slide 25: Hours comparison normative Vs. Actual
Equipment. | Normative |  |  | 2011-12 |  |  | 
 | W/H | M/H | I/H | W/H | M/H | I/H | B/H
SHOVEL |  |  |  |  |  |  | 
5cum/4.6B/5A | 5080.8 | 1752 | 1927.2 | 2164 | 3826.5 | 112 | 2657.5
10cum/1900AL P&H | 5080.8 | 1752 | 1927.2 | 4162.417 | 1689.5 | 1456.083 | 1452
Hydraulic | 5080.8 | 1752 | 1927.2 | 3075.2 | 2144.8 | 312.5 | 2176.3
DUMPER |  |  |  |  |  |  | 
50t(All Dumper) | 4380 | 2890.8 | 1489.2 | 2504.429 | 1101.762 | 424.0238 | 4408.643
BH50M-1 60T | 4380 | 2890.8 | 1489.2 | 3951.1 | 1578 | 567.6 | 1434.5
BH100 100T | 4380 | 2890.8 | 1489.2 | 1515.204 | 1902.5 | 542 | 1152.222
120t/445E | 4818 | 2452.8 | 1489.2 | 1307.631 | 1030.292 | 362.9914 | 3860.781

## Slide 26: Equipment wise production performance-SONEPUR BAZARI
EQIPMENT | Total Trips |  |  |  |  |  | Productivity |  |  |  | 
 | COAL |  |  | OB |  |  | TOTAL (CU. M.) | Assessed cap.( M. Cum.) |  |  | % Ach.
 | 35T | 50T | 120T | 35T | 50T | 120T |  | UNIT CAP. | ROLL | TOTAL CAP. | 
10 cum. shovel | 0 | 4099 | 7867 | 0 | 8264 | 127160 | 5598758 | 1.89 | 6 | 11.34 | 49.37
5/4.6 Cum. shovel | 0 | 644 | 0 | 0 | 9961 | 0 | 210490 | 0.89 | 2 | 1.78 | 11.83
Hyd. Shovel TOTAL | 0 | 62166 | 193 | 0 | 25716 | 0 | 1608980 |  |  | 3.57 | 45.13
DUMPER -WISE | 0 | 66909 | 8060 | 0 | 43941 | 127160 | 7418228 |  |  | 13.35 | 55.57
35t | 0 |  |  | 0 |  |  | 0 | 0.095 | 2 | 0.18 | 0.00
50t |  | 66909 |  |  | 43941 |  | 2049728 | 0.118 | 24.5 | 2.90 | 70.66
120t |  |  | 8060 |  |  | 127160 | 5368500 | 0.311 | 33 | 10.27 | 52.28

## Slide 27: Data Analysis:-
General analysis:-
(1)No. of days
(2)System factor is itself less
Reasons:-
Shovel idle hours:-
(A)Management factors-
Delay in starting of shift.
Delay in return from Tiffin break.
Early ending of shift.
(B)External factors(Stoppage of Shovel)
Land dispute with villagers
Short supply of explosives.
Power supply

## Slide 28
(C)Job factors:-
Low explosive supply(Hourly productivity)
Frequent blasting
Inexperienced operator
Improper fragmentation
Maintenance and breakdown of Shovel
Maintenance schedule is not followed.
Poor spare management and delay in procurement of spares.
Dumper Analysis:-
(A)Extra Dumper
(B)Haulage road –High gradient than 1in16
-Not paved
-Slushy due to rain and alluvium layer.

## Slide 29: Conclusion and Recommendation:-
System factor should not be lower than 0.85.
Dumper factor should be equal to1.
Separate equipments to be used for COAL/OB.
Hot seat change to be implemented.
Maintenance to be outsourced to the company.
Haulage road consideration.
Blasting should be in big rounds.
Miscellaneous issues (like land, explosive, power)should be resolved.